## Dashboard
NetLabz Enterprise — Project Tracker
Overall Progress | 12.96% |  | Status | Meaning
Total Tasks | 216 |  | Not Started | Task has not been started.
Complete | 28 |  | In Progress | Actively working on the task.
In Progress | 0 |  | Blocked | Cannot proceed until another issue is resolved.
Blocked | 2 |  | Complete | Task and required evidence are finished.
Not Started | 185 |  | Skipped | Intentionally omitted; explain why in Notes.
Phase # | Phase | Difficulty | Total | Complete | In Progress | Blocked | Progress
0 | Hyper-V Host Baseline & GitHub | Beginner | 14 | 14 | 0 | 0 | 100%
1 | Virtual Switching & Isolated Test Network | Beginner | 9 | 6 | 0 | 2 | 66.67%
2 | Firewall / Router VM | Intermediate | 10 | 8 | 0 | 0 | 80%
3 | Windows Server DC01 | Intermediate | 10 | 0 | 0 | 0 | 0%
4 | Windows Client & Active Directory | Intermediate | 10 | 0 | 0 | 0 | 0%
5 | DNS & DHCP Laboratory | Intermediate | 10 | 0 | 0 | 0 | 0%
6 | Multi-Subnet Routing | Intermediate | 10 | 0 | 0 | 0 | 0%
7 | Linux Server | Intermediate | 10 | 0 | 0 | 0 | 0%
8 | Docker Containers | Intermediate | 10 | 0 | 0 | 0 | 0%
9 | Firewall Policies & DMZ | Intermediate | 10 | 0 | 0 | 0 | 0%
10 | VLAN Implementation | Advanced | 11 | 0 | 0 | 0 | 0%
11 | IPv6 | Advanced | 10 | 0 | 0 | 0 | 0%
12 | Monitoring & Logging | Intermediate | 10 | 0 | 0 | 0 | 0%
13 | PowerShell Automation | Intermediate | 10 | 0 | 0 | 0 | 0%
14 | Bash Automation | Intermediate | 8 | 0 | 0 | 0 | 0%
15 | Python Tooling | Intermediate | 9 | 0 | 0 | 0 | 0%
16 | Ansible | Advanced | 10 | 0 | 0 | 0 | 0%
17 | Backup & Disaster Recovery | Intermediate | 10 | 0 | 0 | 0 | 0%
18 | VPN | Advanced | 9 | 0 | 0 | 0 | 0%
19 | Cloud Integration | Advanced | 11 | 0 | 0 | 0 | 0%
20 | Full Break/Fix Exercises | Advanced | 15 | 0 | 0 | 0 | 0%

## Project Checklist
Master Project Checklist
Task ID | Phase # | Phase | Category | Task | Deliverable / Evidence | Status | Priority | Notes
P00-01 | 0 | Hyper-V Host Baseline & GitHub | Host | Record OptiPlex CPU, RAM, storage, NIC, Windows version, and current hostname. | docs/host-baseline.md with command output summary | Complete | High
P00-02 | 0 | Hyper-V Host Baseline & GitHub | Host | Verify BIOS/UEFI virtualization support and Hyper-V requirements. | VirtualizationFirmwareEnabled confirmed; note result in baseline | Complete | High
P00-03 | 0 | Hyper-V Host Baseline & GitHub | Hyper-V | Verify Hyper-V feature is enabled and Hyper-V Manager opens correctly. | Screenshot or command output documented | Complete | High
P00-04 | 0 | Hyper-V Host Baseline & GitHub | Hyper-V | Inventory any existing VMs and virtual switches before making changes. | Get-VM and Get-VMSwitch results summarized | Complete | High
P00-05 | 0 | Hyper-V Host Baseline & GitHub | Standards | Choose/confirm Hyper-V host name (recommended HYPV01). | Hostname recorded in naming standard | Complete | Medium
P00-06 | 0 | Hyper-V Host Baseline & GitHub | Git | Install/verify Git and configure user.name and user.email. | git --version and config verified | Complete | High
P00-07 | 0 | Hyper-V Host Baseline & GitHub | Git | Create local repository folder C:\Labs\hyperv-enterprise-lab. | Repository folder exists | Complete | High
P00-08 | 0 | Hyper-V Host Baseline & GitHub | Git | Create README.md, docs, diagrams, hyper-v, scripts, and incidents structure. | Repository tree visible in Git | Complete | High
P00-09 | 0 | Hyper-V Host Baseline & GitHub | Security | Create .gitignore that excludes VHD/VHDX, ISOs, secrets, logs, and packet captures as appropriate. | Committed .gitignore | Complete | High | Used AI to list file types that are common with VM's so as not to miss any, creating vulnerability.
P00-10 | 0 | Hyper-V Host Baseline & GitHub | Standards | Document VM, switch, server, client, and network naming conventions. | docs/naming-standard.md | Complete | High
P00-11 | 0 | Hyper-V Host Baseline & GitHub | Standards | Document initial IPv4 network and address allocation plan. | docs/ip-address-plan.md | Complete | High
P00-12 | 0 | Hyper-V Host Baseline & GitHub | Git | Initialize Git, stage files, and create the first meaningful commit. | Commit: Initialize Hyper-V enterprise lab repository | Complete | High
P00-13 | 0 | Hyper-V Host Baseline & GitHub | GitHub | Create a public GitHub repository and push the local repository. | GitHub repository reachable and README renders | Complete | High
P00-14 | 0 | Hyper-V Host Baseline & GitHub | Documentation | Add project purpose, goals, hardware, and planned architecture to README. | README explains project to an employer | Complete | Medium
P01-01 | 1 | Virtual Switching & Isolated Test Network | Concepts | Document the difference between External, Internal, and Private Hyper-V switches. | Short comparison in hyper-v/virtual-switches.md | Complete | High
P01-02 | 1 | Virtual Switching & Isolated Test Network | Hyper-V | Create the first isolated virtual switch for lab-only communication. | vSW-LAB or equivalent exists | Complete | High | Created all my vswitches 1x External, 3x Internal
P01-03 | 1 | Virtual Switching & Isolated Test Network | VM | Create two lightweight test VMs with conservative memory allocations. | Two test VMs boot successfully | Complete | High
P01-04 | 1 | Virtual Switching & Isolated Test Network | Networking | Assign static IPv4 addresses on the same test subnet. | Both VMs have documented addresses | Complete | High
P01-05 | 1 | Virtual Switching & Isolated Test Network | Testing | Verify same-subnet connectivity with ping and ARP neighbor tables. | Successful ICMP and ARP observations recorded | Complete | High
P01-06 | 1 | Virtual Switching & Isolated Test Network | Wireshark | Capture ARP request/reply traffic and identify source/destination MAC addresses. | Annotated screenshot or notes | Blocked | Medium | Would need to install wireshark inside VM to capture arp and icmp unicast replies. Currently only captures broadcasts.
P01-07 | 1 | Virtual Switching & Isolated Test Network | Wireshark | Capture ICMP echo request/reply and map it to OSI layers. | Packet capture observations documented | Skipped | Medium
P01-08 | 1 | Virtual Switching & Isolated Test Network | Troubleshooting | Break connectivity with an incorrect subnet mask and diagnose before fixing it. | Mini incident note with root cause and validation | Blocked | Medium | No routing capabilities yet, so adding this section later.
P01-09 | 1 | Virtual Switching & Isolated Test Network | Git | Commit the network diagram, switch configuration notes, and test results. | Phase 1 Git commit(s) | Complete | High
P02-01 | 2 | Firewall / Router VM | Firewall | Select OPNsense or pfSense and document why it was chosen. | Decision recorded in docs/firewall-design.md | Complete | High | Selecting OPNSense
P02-02 | 2 | Firewall / Router VM | VM | Create FW01 with appropriate CPU/RAM/disk and multiple virtual NICs. | FW01 VM configuration documented | Complete | High
P02-03 | 2 | Firewall / Router VM | Networking | Connect FW01 WAN to controlled external/home access and LAN to the isolated lab. | WAN/LAN mapping diagram | Complete | High
P02-04 | 2 | Firewall / Router VM | Addressing | Assign initial LAN gateway address 10.10.20.1/24 | Gateway responds from lab host | Complete | High
P02-05 | 2 | Firewall / Router VM | Routing | Enable lab clients to reach their default gateway. | Ping/traceroute validation | Complete | High
P02-06 | 2 | Firewall / Router VM | NAT | Configure outbound NAT so lab systems can reach the internet without direct exposure. | Internet access works from test VM | Complete | High
P02-07 | 2 | Firewall / Router VM | Security | Create rules preventing lab-initiated access to protected home network ranges. | Firewall rule screenshots/config notes | Complete | High
P02-08 | 2 | Firewall / Router VM | Testing | Validate internet, DNS, gateway, and home-network isolation behavior. | Connectivity matrix documented | Complete | High
P02-09 | 2 | Firewall / Router VM | Troubleshooting | Create and repair one intentional firewall rule failure. | Incident note showing logs and fix | Not Started | Medium
P02-10 | 2 | Firewall / Router VM | Git | Commit sanitized firewall architecture and rule documentation. | Phase 2 Git commit(s) | Not Started | High
P03-01 | 3 | Windows Server DC01 | Windows Server | Download a Windows Server evaluation ISO and record the source/version. | ISO source and version documented; ISO excluded from Git | Not Started | High
P03-02 | 3 | Windows Server DC01 | VM | Create DC01 with conservative CPU/RAM/disk settings. | DC01 VM build sheet | Not Started | High
P03-03 | 3 | Windows Server DC01 | Networking | Assign DC01 a static server-network address (planned 10.10.10.10). | IP configuration documented | Not Started | High
P03-04 | 3 | Windows Server DC01 | Windows Server | Rename the server DC01 and install updates. | Hostname/update state recorded | Not Started | Medium
P03-05 | 3 | Windows Server DC01 | AD DS | Install Active Directory Domain Services. | Role installation documented | Not Started | High
P03-06 | 3 | Windows Server DC01 | AD DS | Create the lab forest/domain using the chosen lab domain name. | Domain name documented | Not Started | High
P03-07 | 3 | Windows Server DC01 | DNS | Install/verify AD-integrated DNS and inspect default zones/records. | DNS zones and key records documented | Not Started | High
P03-08 | 3 | Windows Server DC01 | Validation | Verify DC01 resolves itself correctly and basic AD health checks pass. | dcdiag/DNS test results summarized | Not Started | High
P03-09 | 3 | Windows Server DC01 | Checkpoint | Create a known-good checkpoint or backup point after core domain deployment. | Recovery point recorded | Not Started | Medium
P03-10 | 3 | Windows Server DC01 | Git | Commit the DC01 build documentation without secrets. | Phase 3 Git commit(s) | Not Started | High
P04-01 | 4 | Windows Client & Active Directory | VM | Create CLIENT01 as a Windows client VM. | CLIENT01 build sheet | Not Started | High
P04-02 | 4 | Windows Client & Active Directory | Networking | Place CLIENT01 on the intended client/test network and configure DNS to use DC01. | ipconfig output and diagram updated | Not Started | High
P04-03 | 4 | Windows Client & Active Directory | AD | Join CLIENT01 to the domain. | Domain join succeeds | Not Started | High
P04-04 | 4 | Windows Client & Active Directory | AD | Create a small enterprise-style OU structure. | OU diagram or documented hierarchy | Not Started | Medium
P04-05 | 4 | Windows Client & Active Directory | AD | Create representative users and security groups for IT, Operations, and Accounting. | Users/groups documented with no real personal data | Not Started | Medium
P04-06 | 4 | Windows Client & Active Directory | AD | Test domain user logon to CLIENT01. | Successful domain logon evidence | Not Started | High
P04-07 | 4 | Windows Client & Active Directory | GPO | Create one basic GPO and verify it applies to CLIENT01. | gpresult evidence and policy documentation | Not Started | Medium
P04-08 | 4 | Windows Client & Active Directory | Authentication | Observe Kerberos-related logon behavior/events at a basic level. | Relevant event IDs/notes captured | Not Started | Medium
P04-09 | 4 | Windows Client & Active Directory | Troubleshooting | Break domain access by changing client DNS, diagnose, and restore it. | Incident note | Not Started | High
P04-10 | 4 | Windows Client & Active Directory | Git | Commit AD structure, client build, and sanitized screenshots/notes. | Phase 4 Git commit(s) | Not Started | High
P05-01 | 5 | DNS & DHCP Laboratory | DNS | Create forward lookup records and test A/AAAA/CNAME behavior as applicable. | Record table and nslookup/Resolve-DnsName output | Not Started | High
P05-02 | 5 | DNS & DHCP Laboratory | DNS | Create and test a reverse lookup zone/PTR record. | Reverse resolution validation | Not Started | Medium
P05-03 | 5 | DNS & DHCP Laboratory | DNS | Use nslookup, Resolve-DnsName, and dig from supported hosts. | Command examples documented | Not Started | High
P05-04 | 5 | DNS & DHCP Laboratory | Wireshark | Capture a DNS query/response and identify transaction ID, query type, and answer. | Annotated DNS capture notes | Not Started | High
P05-05 | 5 | DNS & DHCP Laboratory | DHCP | Deploy DHCP on the selected server/firewall according to the design. | DHCP service documented | Not Started | High
P05-06 | 5 | DNS & DHCP Laboratory | DHCP | Create a client scope using the planned DHCP range. | Scope configuration recorded | Not Started | High
P05-07 | 5 | DNS & DHCP Laboratory | DHCP | Configure gateway and DNS options and obtain a lease from CLIENT01. | ipconfig /all shows expected options | Not Started | High
P05-08 | 5 | DNS & DHCP Laboratory | Wireshark | Capture and explain DHCP DORA. | Discover/Offer/Request/Ack evidence | Not Started | High
P05-09 | 5 | DNS & DHCP Laboratory | Troubleshooting | Test a wrong DNS server, exhausted/disabled DHCP scope, or wrong option and repair it. | Incident report with symptoms/root cause | Not Started | High
P05-10 | 5 | DNS & DHCP Laboratory | Git | Commit protocol captures as notes/screenshots and update network documentation. | Phase 5 Git commit(s) | Not Started | Medium
P06-01 | 6 | Multi-Subnet Routing | Design | Create separate Server and Client subnets using Hyper-V virtual switches/interfaces. | Updated logical topology | Not Started | High
P06-02 | 6 | Multi-Subnet Routing | Routing | Add FW01 interfaces/gateways for 10.10.10.0/24 and 10.10.20.0/24. | Interface table documented | Not Started | High
P06-03 | 6 | Multi-Subnet Routing | Routing | Configure hosts with the correct default gateways. | Address plan reflects actual configuration | Not Started | High
P06-04 | 6 | Multi-Subnet Routing | Testing | Verify same-subnet and cross-subnet ICMP behavior. | Connectivity matrix | Not Started | High
P06-05 | 6 | Multi-Subnet Routing | Tools | Use tracert/traceroute to verify the Layer 3 path. | Traceroute examples documented | Not Started | High
P06-06 | 6 | Multi-Subnet Routing | Firewall | Explicitly allow only required initial inter-subnet traffic. | Firewall policy table | Not Started | High
P06-07 | 6 | Multi-Subnet Routing | Wireshark | Capture traffic before and after routing and explain MAC/IP changes across hops. | Packet-flow diagram | Not Started | Medium
P06-08 | 6 | Multi-Subnet Routing | Troubleshooting | Introduce an incorrect gateway or missing route and diagnose it. | Incident report | Not Started | High
P06-09 | 6 | Multi-Subnet Routing | Packet Tracer | Recreate an equivalent routed topology in Cisco Packet Tracer. | Packet Tracer file/screenshot referenced | Not Started | Medium
P06-10 | 6 | Multi-Subnet Routing | Git | Commit routing diagrams, policy table, and troubleshooting notes. | Phase 6 Git commit(s) | Not Started | High
P07-01 | 7 | Linux Server | VM | Create LINUX01 using Ubuntu Server or another chosen Linux distribution. | LINUX01 build sheet | Not Started | High
P07-02 | 7 | Linux Server | Linux | Perform package updates and document package-management commands. | apt/dnf usage notes | Not Started | Medium
P07-03 | 7 | Linux Server | Linux | Configure hostname, static/dynamic networking, DNS, and default route. | ip addr/ip route/resolvectl output summarized | Not Started | High
P07-04 | 7 | Linux Server | Linux | Create non-root admin user and practice sudo. | User/admin procedure documented | Not Started | High
P07-05 | 7 | Linux Server | Linux | Configure and test SSH from an administrative machine. | SSH connection succeeds | Not Started | High
P07-06 | 7 | Linux Server | Linux | Practice ip, ss, ping, traceroute, dig, curl, journalctl, and systemctl. | Linux command cheat sheet in repo | Not Started | High
P07-07 | 7 | Linux Server | Security | Configure the Linux firewall at a basic level and verify allowed/blocked traffic. | Firewall rules/tests documented | Not Started | Medium
P07-08 | 7 | Linux Server | Wireshark | Capture SSH/TCP session setup and explain what remains visible despite encryption. | Capture observations | Not Started | Medium
P07-09 | 7 | Linux Server | Troubleshooting | Break DNS, route, service, or firewall configuration and recover it. | Linux incident report | Not Started | High
P07-10 | 7 | Linux Server | Git | Commit Linux build and administration notes. | Phase 7 Git commit(s) | Not Started | High
P08-01 | 8 | Docker Containers | Concepts | Document VM vs container differences: kernel, isolation, portability, resource use. | containers/README.md comparison | Not Started | High
P08-02 | 8 | Docker Containers | Docker | Install Docker Engine on LINUX01 or dedicated DOCKER01. | Installation steps documented | Not Started | High
P08-03 | 8 | Docker Containers | Docker | Run a simple container and inspect image/container lifecycle. | docker ps/images/inspect notes | Not Started | High
P08-04 | 8 | Docker Containers | Docker | Map a container port and access the service across the lab network. | Reachable test application | Not Started | High
P08-05 | 8 | Docker Containers | Docker | Create a persistent volume and prove data survives container recreation. | Persistence test documented | Not Started | Medium
P08-06 | 8 | Docker Containers | Docker | Create a custom Docker network and inspect container addressing. | Network inspection notes | Not Started | Medium
P08-07 | 8 | Docker Containers | Compose | Deploy a multi-container application with Docker Compose. | compose.yaml committed | Not Started | High
P08-08 | 8 | Docker Containers | Security | Keep secrets out of Git and demonstrate use of environment/example configuration. | Sanitized .env.example or documentation | Not Started | High
P08-09 | 8 | Docker Containers | Troubleshooting | Break a port mapping, container network, or volume and repair it. | Container incident report | Not Started | Medium
P08-10 | 8 | Docker Containers | Git | Commit Docker/Compose configuration and diagrams. | Phase 8 Git commit(s) | Not Started | High
P09-01 | 9 | Firewall Policies & DMZ | Design | Create the DMZ subnet 10.10.30.0/24 and document its purpose/trust boundary. | DMZ architecture diagram | Not Started | High
P09-02 | 9 | Firewall Policies & DMZ | Networking | Attach a DMZ interface/network to FW01. | FW01 interface table updated | Not Started | High
P09-03 | 9 | Firewall Policies & DMZ | Service | Place a test web/container service in the DMZ. | Service reachable according to policy | Not Started | High
P09-04 | 9 | Firewall Policies & DMZ | Firewall | Create explicit Client→DMZ, Server→DMZ, DMZ→Server, and DMZ→Internet policies. | Firewall matrix | Not Started | High
P09-05 | 9 | Firewall Policies & DMZ | Security | Apply default-deny/least-privilege logic between trust zones. | Policy rationale documented | Not Started | High
P09-06 | 9 | Firewall Policies & DMZ | Testing | Validate both allowed and denied flows with Test-NetConnection/curl/nc. | Connectivity matrix | Not Started | High
P09-07 | 9 | Firewall Policies & DMZ | Logging | Use firewall logs to confirm why a blocked flow was denied. | Log evidence documented | Not Started | Medium
P09-08 | 9 | Firewall Policies & DMZ | Wireshark | Capture an allowed TCP connection and a blocked/failed connection. | Packet comparison notes | Not Started | Medium
P09-09 | 9 | Firewall Policies & DMZ | Troubleshooting | Create an INC ticket for an incorrect DMZ firewall rule and resolve it. | Incident report | Not Started | High
P09-10 | 9 | Firewall Policies & DMZ | Git | Commit DMZ topology and sanitized firewall policies. | Phase 9 Git commit(s) | Not Started | High
P10-01 | 10 | VLAN Implementation | Concepts | Document access ports, trunk ports, VLAN IDs, native/untagged traffic, and 802.1Q. | VLAN concepts note | Not Started | High
P10-02 | 10 | VLAN Implementation | Design | Assign VLAN IDs to Server, Client, DMZ, Management, and future networks. | VLAN table | Not Started | High
P10-03 | 10 | VLAN Implementation | Hyper-V | Design how VLAN tagging will be represented in Hyper-V. | Updated switch/NIC diagram | Not Started | High
P10-04 | 10 | VLAN Implementation | Hyper-V | Implement VLAN tagging on selected virtual NICs/switch paths. | VLAN config documented | Not Started | High
P10-05 | 10 | VLAN Implementation | Firewall | Create VLAN interfaces/subinterfaces on FW01 as required. | Interface table | Not Started | High
P10-06 | 10 | VLAN Implementation | Testing | Verify same-VLAN connectivity and inter-VLAN routing. | Test matrix | Not Started | High
P10-07 | 10 | VLAN Implementation | Troubleshooting | Create a VLAN ID mismatch and diagnose the resulting isolation. | Incident report | Not Started | High
P10-08 | 10 | VLAN Implementation | Packet Tracer | Build a matching Cisco switch/router VLAN + trunk lab. | Packet Tracer artifact referenced | Not Started | High
P10-09 | 10 | VLAN Implementation | Wireshark | Observe 802.1Q tags where the capture point exposes them. | Capture note or explanation if tags are offloaded/hidden | Not Started | Medium
P10-10 | 10 | VLAN Implementation | Hardware | Decide whether a managed switch/second NIC is now justified; document the decision. | Hardware decision record | Not Started | Medium
P10-11 | 10 | VLAN Implementation | Git | Commit VLAN plan, configs, diagrams, and troubleshooting notes. | Phase 10 Git commit(s) | Not Started | High
P11-01 | 11 | IPv6 | Concepts | Review IPv6 notation, prefix length, link-local, global unicast, multicast, and SLAAC concepts. | IPv6 reference notes | Not Started | High
P11-02 | 11 | IPv6 | Addressing | Create an IPv6 lab addressing plan without using production/home prefixes. | docs/ipv6-address-plan.md | Not Started | High
P11-03 | 11 | IPv6 | Networking | Enable IPv6 on selected lab networks and verify link-local communication. | ipconfig/ip addr evidence | Not Started | High
P11-04 | 11 | IPv6 | Routing | Configure IPv6 routing across at least two lab networks. | Cross-subnet IPv6 test | Not Started | High
P11-05 | 11 | IPv6 | DNS | Create/test AAAA records and IPv6 name resolution. | DNS validation | Not Started | Medium
P11-06 | 11 | IPv6 | Tools | Use ping -6, tracert/traceroute IPv6, and relevant neighbor commands. | Command output documented | Not Started | Medium
P11-07 | 11 | IPv6 | Wireshark | Capture Neighbor Discovery and ICMPv6 traffic. | NDP/ICMPv6 observations | Not Started | High
P11-08 | 11 | IPv6 | Security | Confirm firewall policies handle IPv6 explicitly rather than assuming IPv4 rules apply. | IPv6 rule review | Not Started | High
P11-09 | 11 | IPv6 | Troubleshooting | Break an IPv6 prefix/gateway/DNS setting and diagnose it. | Incident report | Not Started | Medium
P11-10 | 11 | IPv6 | Git | Commit IPv6 plan, packet notes, and diagrams. | Phase 11 Git commit(s) | Not Started | High
P12-01 | 12 | Monitoring & Logging | Design | Define what must be monitored: host, VMs, firewall, Windows, Linux, containers, network services. | Monitoring requirements document | Not Started | High
P12-02 | 12 | Monitoring & Logging | Monitoring | Deploy MON01 or a lightweight monitoring/logging stack appropriate to RAM limits. | MON01 build/config documentation | Not Started | High
P12-03 | 12 | Monitoring & Logging | Windows | Forward or centralize selected Windows events/logs. | Windows log visibility demonstrated | Not Started | Medium
P12-04 | 12 | Monitoring & Logging | Linux | Forward syslog/journal data or expose health metrics from Linux. | Linux visibility demonstrated | Not Started | Medium
P12-05 | 12 | Monitoring & Logging | Firewall | Send or inspect FW01 logs centrally where feasible. | Firewall events visible | Not Started | Medium
P12-06 | 12 | Monitoring & Logging | Containers | Monitor basic container status/resource/service health. | Container health view | Not Started | Medium
P12-07 | 12 | Monitoring & Logging | Network | Create checks for DNS, HTTP/HTTPS, ICMP, and selected TCP ports. | Service checks documented | Not Started | High
P12-08 | 12 | Monitoring & Logging | Alerting | Create at least one useful alert or failure indication. | Alert screenshot/record | Not Started | Medium
P12-09 | 12 | Monitoring & Logging | Failure Test | Stop a service and confirm monitoring detects the outage and recovery. | Outage timeline documented | Not Started | High
P12-10 | 12 | Monitoring & Logging | Git | Commit monitoring architecture, configs that are safe to publish, and screenshots. | Phase 12 Git commit(s) | Not Started | High
P13-01 | 13 | PowerShell Automation | PowerShell | Create a scripts/powershell README with purpose and execution requirements. | Script catalog | Not Started | Medium
P13-02 | 13 | PowerShell Automation | PowerShell | Write a Hyper-V inventory script for VMs, switches, CPU, memory, and state. | Reusable .ps1 committed | Not Started | High
P13-03 | 13 | PowerShell Automation | PowerShell | Write a network health-check script using Test-Connection/Test-NetConnection/Resolve-DnsName. | Health-check .ps1 committed | Not Started | High
P13-04 | 13 | PowerShell Automation | PowerShell | Write an AD inventory/reporting script for users, groups, computers, or OUs. | AD reporting script | Not Started | Medium
P13-05 | 13 | PowerShell Automation | PowerShell | Export script results to CSV or structured output. | Sample sanitized output | Not Started | Medium
P13-06 | 13 | PowerShell Automation | PowerShell | Add parameters, validation, comments/help, and useful error handling to at least one script. | Improved script quality evidence | Not Started | High
P13-07 | 13 | PowerShell Automation | Git | Develop one script on a feature branch and merge it into main. | Branch/merge history visible | Not Started | High
P13-08 | 13 | PowerShell Automation | Testing | Test scripts against expected success and failure conditions. | Test notes | Not Started | Medium
P13-09 | 13 | PowerShell Automation | Documentation | Add usage examples to README without hard-coded secrets or personal paths. | Documented examples | Not Started | High
P13-10 | 13 | PowerShell Automation | Git | Tag or mark a Phase 13 milestone release/commit. | Phase 13 milestone | Not Started | Medium
P14-01 | 14 | Bash Automation | Bash | Create a Bash script directory README and coding conventions. | Bash script catalog | Not Started | Medium
P14-02 | 14 | Bash Automation | Bash | Write a Linux network health script using ping, ip, ss, dig, and curl. | health-check.sh | Not Started | High
P14-03 | 14 | Bash Automation | Bash | Write a service-status script using systemctl and journalctl. | service-check.sh | Not Started | Medium
P14-04 | 14 | Bash Automation | Bash | Use variables, conditionals, loops, functions, and exit codes. | Script demonstrates core Bash structures | Not Started | High
P14-05 | 14 | Bash Automation | Bash | Write output to a timestamped report/log. | Sample sanitized output | Not Started | Medium
P14-06 | 14 | Bash Automation | Bash | Schedule one safe task with cron/systemd timer. | Scheduled task documentation | Not Started | Medium
P14-07 | 14 | Bash Automation | Troubleshooting | Handle an unreachable host or failed service gracefully in the script. | Error handling demonstrated | Not Started | High
P14-08 | 14 | Bash Automation | Git | Commit scripts incrementally with meaningful messages. | Phase 14 Git history | Not Started | High
P15-01 | 15 | Python Tooling | Python | Create and use a Python virtual environment; exclude it from Git. | venv workflow documented | Not Started | Medium
P15-02 | 15 | Python Tooling | Python | Build a simple subnet/IP validation or inventory utility. | Python utility committed | Not Started | High
P15-03 | 15 | Python Tooling | Python | Build a TCP/service reachability checker using sockets or standard libraries. | Service checker committed | Not Started | High
P15-04 | 15 | Python Tooling | Python | Parse structured data such as CSV/JSON produced by lab systems/scripts. | Parser/report script | Not Started | Medium
P15-05 | 15 | Python Tooling | Python | Generate a readable infrastructure health or inventory report. | Sample sanitized report | Not Started | High
P15-06 | 15 | Python Tooling | Python | Add argparse/input validation and exception handling. | CLI behavior documented | Not Started | Medium
P15-07 | 15 | Python Tooling | Testing | Create basic tests or repeatable test cases for one utility. | Test file or documented cases | Not Started | Medium
P15-08 | 15 | Python Tooling | Security | Ensure scripts do not embed credentials/tokens. | Security review complete | Not Started | High
P15-09 | 15 | Python Tooling | Git | Develop and merge the Python utility through normal Git workflow. | Phase 15 branch/commit history | Not Started | High
P16-01 | 16 | Ansible | Ansible | Create/prepare an Ansible control node on Linux. | Control node documented | Not Started | High
P16-02 | 16 | Ansible | Ansible | Create an inventory file for Linux and other manageable hosts. | Sanitized inventory committed | Not Started | High
P16-03 | 16 | Ansible | Ansible | Configure SSH key authentication for Linux management. | Key-based management works; private key excluded | Not Started | High
P16-04 | 16 | Ansible | Ansible | Run ad-hoc ping/fact-gathering commands against managed Linux nodes. | Successful ad-hoc output | Not Started | High
P16-05 | 16 | Ansible | Ansible | Create a playbook that installs/configures a simple package or service. | First playbook committed | Not Started | High
P16-06 | 16 | Ansible | Ansible | Use variables and templates in a playbook. | Variable/template example | Not Started | Medium
P16-07 | 16 | Ansible | Ansible | Make a playbook idempotent and prove a second run reports no unnecessary changes. | Two-run comparison | Not Started | High
P16-08 | 16 | Ansible | Ansible | Explore supported Windows management from Ansible if resources permit. | Windows automation notes/playbook | Not Started | Medium
P16-09 | 16 | Ansible | Troubleshooting | Break SSH/inventory/permissions and diagnose an Ansible failure. | Incident/troubleshooting note | Not Started | Medium
P16-10 | 16 | Ansible | Git | Commit playbooks, roles/configs, and documentation safely. | Phase 16 Git commit(s) | Not Started | High
P17-01 | 17 | Backup & Disaster Recovery | Design | Define RPO/RTO-style goals for key lab services in plain language. | Backup/DR plan | Not Started | Medium
P17-02 | 17 | Backup & Disaster Recovery | Hyper-V | Create a backup/export strategy for critical VMs. | Backup procedure | Not Started | High
P17-03 | 17 | Backup & Disaster Recovery | AD | Document safe recovery considerations for DC01 and domain services. | AD recovery notes | Not Started | High
P17-04 | 17 | Backup & Disaster Recovery | Linux | Back up selected Linux configuration/application data. | Backup artifact/process | Not Started | Medium
P17-05 | 17 | Backup & Disaster Recovery | Docker | Back up container configuration and persistent volumes/data. | Container backup procedure | Not Started | Medium
P17-06 | 17 | Backup & Disaster Recovery | Configuration | Store infrastructure documentation/scripts/configs in Git as the configuration record. | Repo reflects current state | Not Started | High
P17-07 | 17 | Backup & Disaster Recovery | Recovery | Delete/disable a noncritical test service and restore it from backup/configuration. | Successful recovery evidence | Not Started | High
P17-08 | 17 | Backup & Disaster Recovery | Recovery | Restore a test VM or exported copy and validate networking/services. | Restore test report | Not Started | High
P17-09 | 17 | Backup & Disaster Recovery | Validation | Document what checkpoints can and cannot replace in a real backup strategy. | DR lessons learned | Not Started | Medium
P17-10 | 17 | Backup & Disaster Recovery | Git | Commit backup/restore runbooks and results. | Phase 17 Git commit(s) | Not Started | High
P18-01 | 18 | VPN | Concepts | Document site-to-site vs remote-access VPN, tunneling, encryption, and authentication concepts. | VPN design notes | Not Started | High
P18-02 | 18 | VPN | Design | Choose a safe VPN lab scenario that does not expose unnecessary services to the internet. | VPN topology | Not Started | High
P18-03 | 18 | VPN | Firewall | Configure the chosen VPN technology on FW01 or dedicated endpoints. | Sanitized VPN configuration notes | Not Started | High
P18-04 | 18 | VPN | Routing | Configure tunnel routes/allowed networks. | Routing table updated | Not Started | High
P18-05 | 18 | VPN | Security | Apply firewall policies to VPN-originated traffic. | VPN access policy | Not Started | High
P18-06 | 18 | VPN | Testing | Validate permitted services across the tunnel and confirm nonpermitted traffic is blocked. | Connectivity matrix | Not Started | High
P18-07 | 18 | VPN | Wireshark | Compare traffic outside the tunnel with traffic visible after decryption at endpoints. | VPN packet observations | Not Started | Medium
P18-08 | 18 | VPN | Troubleshooting | Break a route, key/certificate setting, or policy and diagnose the tunnel failure. | Incident report | Not Started | High
P18-09 | 18 | VPN | Git | Commit VPN diagrams, sanitized configs, and troubleshooting notes. | Phase 18 Git commit(s) | Not Started | High
P19-01 | 19 | Cloud Integration | Cloud | Create an Azure learning/subscription plan with spending controls before deploying resources. | Budget/safety notes | Not Started | High
P19-02 | 19 | Cloud Integration | Cloud | Create a cloud virtual network and subnets mirroring selected on-prem lab concepts. | Cloud network diagram | Not Started | High
P19-03 | 19 | Cloud Integration | Cloud | Deploy a small test VM or service with minimal cost/resource sizing. | Cloud workload documented | Not Started | Medium
P19-04 | 19 | Cloud Integration | Cloud | Configure network security rules and compare them with FW01 firewall concepts. | NSG/firewall comparison note | Not Started | High
P19-05 | 19 | Cloud Integration | Cloud | Practice cloud DNS/private addressing/name resolution concepts. | DNS test documentation | Not Started | Medium
P19-06 | 19 | Cloud Integration | Identity | Explore Entra ID/cloud identity concepts and compare with on-prem AD DS. | Identity comparison note | Not Started | Medium
P19-07 | 19 | Cloud Integration | Hybrid | Design or implement a safe hybrid connection concept (VPN if feasible). | Hybrid topology/evidence | Not Started | High
P19-08 | 19 | Cloud Integration | Monitoring | Explore cloud monitoring/logging for the deployed workload. | Monitoring evidence | Not Started | Medium
P19-09 | 19 | Cloud Integration | Automation | Use PowerShell, CLI, or later IaC concepts to query/deploy at least one cloud resource. | Automation artifact | Not Started | Medium
P19-10 | 19 | Cloud Integration | Cost | Remove temporary resources and verify no unnecessary billable resources remain. | Cleanup checklist complete | Not Started | High
P19-11 | 19 | Cloud Integration | Git | Commit cloud architecture, sanitized commands/configs, and lessons learned. | Phase 19 Git commit(s) | Not Started | High
P20-01 | 20 | Full Break/Fix Exercises | Incident | DNS failure: client points to wrong DNS server; diagnose with resolver tools and packet capture. | INC-001 report | Not Started | High
P20-02 | 20 | Full Break/Fix Exercises | Incident | DHCP failure: incorrect/disabled scope or wrong option; identify lease symptoms and repair. | INC-002 report | Not Started | High
P20-03 | 20 | Full Break/Fix Exercises | Incident | Routing failure: incorrect gateway/missing route; use traceroute and route tables to repair. | INC-003 report | Not Started | High
P20-04 | 20 | Full Break/Fix Exercises | Incident | Firewall failure: required TCP service blocked between zones; use logs and Test-NetConnection/curl. | INC-004 report | Not Started | High
P20-05 | 20 | Full Break/Fix Exercises | Incident | AD failure: client cannot authenticate because of DNS/time/service issue; isolate root cause. | INC-005 report | Not Started | High
P20-06 | 20 | Full Break/Fix Exercises | Incident | Linux service failure: application stopped or firewall blocks port; use systemctl/journalctl/ss. | INC-006 report | Not Started | High
P20-07 | 20 | Full Break/Fix Exercises | Incident | Container failure: wrong port/volume/network; inspect Docker state and restore service. | INC-007 report | Not Started | Medium
P20-08 | 20 | Full Break/Fix Exercises | Incident | VLAN failure: mismatched VLAN/tagging configuration; trace Layer 2 symptoms. | INC-008 report | Not Started | Medium
P20-09 | 20 | Full Break/Fix Exercises | Incident | Monitoring failure: deliberately stop a service and confirm alert/detection/recovery timeline. | INC-009 report | Not Started | Medium
P20-10 | 20 | Full Break/Fix Exercises | Incident | Backup recovery: restore a failed test workload and validate service dependencies. | INC-010 report | Not Started | High
P20-11 | 20 | Full Break/Fix Exercises | Capstone | Run one multi-fault scenario containing at least three simultaneous issues without prewritten answers. | Capstone incident report | Not Started | High
P20-12 | 20 | Full Break/Fix Exercises | Portfolio | Create a polished final architecture diagram showing physical, logical, security, and cloud boundaries. | Final diagram committed | Not Started | High
P20-13 | 20 | Full Break/Fix Exercises | Portfolio | Rewrite root README as a recruiter-friendly project case study with skills, architecture, screenshots, and lessons learned. | Final README | Not Started | High
P20-14 | 20 | Full Break/Fix Exercises | Portfolio | Review repository for secrets, stale files, poor commit messages, and unclear documentation. | Security/quality review complete | Not Started | High
P20-15 | 20 | Full Break/Fix Exercises | Portfolio | Create a final release/tag marking the completed portfolio version. | v1.0 or equivalent | Not Started | Medium

## Phase Guide
Phase Guide
Move forward when the exit criteria are met—not merely when the software is installed. Every phase should leave behind documentation and version-controlled evidence.
Phase # | Phase | Objective | Prerequisite | Difficulty | Exit Criteria
0 | Hyper-V Host Baseline & GitHub | Establish the host, documentation standards, repository, and lab conventions. | None | Beginner | Host baseline and standards are documented; public GitHub repo exists; first clean commit is pushed.
1 | Virtual Switching & Isolated Test Network | Build the first safe virtual network and observe basic packet behavior. | Phase 0 | Beginner | Two isolated VMs communicate; ARP/ICMP behavior is captured; one basic network fault is diagnosed.
2 | Firewall / Router VM | Create the lab edge and safely separate lab networks from the home network. | Phase 1 | Intermediate | FW01 provides controlled lab internet access while protecting the home network; firewall behavior is documented.
3 | Windows Server DC01 | Deploy the first Windows Server and establish the core domain infrastructure. | Phase 2 | Intermediate | DC01 is a healthy domain controller with AD-integrated DNS and a documented known-good recovery point.
4 | Windows Client & Active Directory | Join a client to the domain and validate authentication, policy, and administration. | Phase 3 | Intermediate | CLIENT01 joins the domain, domain logon works, OUs/users/groups exist, and at least one GPO applies correctly.
5 | DNS & DHCP Laboratory | Understand, test, break, capture, and repair core naming and address services. | Phase 4 | Intermediate | DNS and DHCP work end-to-end; DORA and DNS traffic are captured; at least one core-service failure is repaired.
6 | Multi-Subnet Routing | Route traffic between server, client, and other lab networks with controlled policies. | Phase 5 | Intermediate | Server and client networks route through FW01 with explicit policies; path and packet behavior are documented.
7 | Linux Server | Build Linux administration and networking fundamentals inside the same enterprise lab. | Phase 6 | Intermediate | LINUX01 is manageable by SSH, core networking tools are practiced, and a Linux fault is diagnosed/repaired.
8 | Docker Containers | Learn container fundamentals and deploy services on a Linux Docker host. | Phase 7 | Intermediate | A Docker host runs persistent and networked containers; Compose is used; secrets are excluded from Git.
9 | Firewall Policies & DMZ | Create a DMZ and enforce least-privilege traffic flows. | Phase 8 | Intermediate | A DMZ exists with least-privilege rules; allowed/denied flows are tested and logged.
10 | VLAN Implementation | Move from separate virtual networks to VLAN-based segmentation and tagging. | Phase 9 | Advanced | VLAN segmentation and inter-VLAN routing work in the lab; an equivalent Cisco Packet Tracer lab is documented.
11 | IPv6 | Add IPv6 addressing, routing, DNS, and troubleshooting alongside IPv4. | Phase 10 | Advanced | IPv6 works across selected lab networks; DNS, NDP/ICMPv6, routing, and firewall behavior are validated.
12 | Monitoring & Logging | Centralize infrastructure visibility, logs, health checks, and basic alerting. | Phase 11 | Intermediate | Core infrastructure and services can be monitored; at least one outage triggers visible detection and recovery.
13 | PowerShell Automation | Automate Windows and Hyper-V administration using reusable scripts. | Phase 12 | Intermediate | Reusable PowerShell scripts automate inventory/health/admin tasks and are developed with a real Git branch workflow.
14 | Bash Automation | Automate Linux administration and operational checks with Bash. | Phase 13 | Intermediate | Bash scripts perform Linux health/service checks with logging, scheduling, and error handling.
15 | Python Tooling | Build simple infrastructure utilities for validation, parsing, and reporting. | Phase 14 | Intermediate | Python utilities validate or report on lab infrastructure with CLI input, error handling, and basic testing.
16 | Ansible | Introduce configuration management and repeatable multi-system administration. | Phase 15 | Advanced | Ansible manages at least one Linux service idempotently across managed hosts; inventory and playbooks are versioned.
17 | Backup & Disaster Recovery | Protect the lab and prove that services can be restored from failure. | Phase 16 | Intermediate | Critical lab services have documented backups and at least one VM/service restore has been successfully tested.
18 | VPN | Implement secure remote/site-style connectivity and inspect encrypted tunnel behavior. | Phase 17 | Advanced | A secure VPN scenario works with controlled routing/policy; a tunnel failure is diagnosed and documented.
19 | Cloud Integration | Extend the lab into Azure-style hybrid infrastructure concepts. | Phase 18 | Advanced | A small cloud environment mirrors lab networking/security concepts; costs are controlled and cleanup is verified.
20 | Full Break/Fix Exercises | Run end-to-end incidents that combine networking, systems, security, and documentation. | Phase 19 | Advanced | Ten structured incidents plus one multi-fault capstone are completed; final architecture and recruiter-ready README are published.

## Sheet1
Network | Subnet | Gateway
Server | 10.10.10.0/24 | 10.10.10.1
Client | 10.10.20.0/24 | 10.10.20.1
DMZ | 10.10.30.0/24 | 10.10.30.1
Management | 10.10.40.0/24 | 10.10.40.1
Monitoring | 10.10.50.0/24 | 10.10.50.1
Security | 10.10.60.0/24 | 10.10.60.1
Containers | 10.10.70.0/24 | 10.10.70.1
Address Range | Use
.1 | Default gateway
.2-.9 | Network infrastructure
.10-.29 | Servers
.30-.49 | Management / infrastructure
.50-.99 | Reserved / static
.100-.199 | DHCP clients
.200-.239 | Lab / testing